## Requirements
S.No | Task Description | Responsible | Status | Remarks
1 | After entering Inventory Id and then press enter, data should be loaded from database. | Soma | Completed
2 | Issue with printing KV diamonds invoice form due to font issue, text is overlapping on the borders | Soma | Not yet Started
3 | New feature for displaying inventory cycle count | Soma | Not yet Started | Need clarification on this requirement
4 | New report for displaying inventory details by category name | Soma | Not yet Started
5 | New report for displaying customer wise sales | Soma | Not yet Started | No customer master is available.
6 | In Invoice details table, add two new columns "CASH", "Credit Card" before the "Price" column | Soma | Not yet Started
7 | New report for displaying pending balance details from customers | Soma | Not yet Started
8 | Add logout option | Soma | Not yet Started
9 | Remove the application restriction on the different computers. | Soma | In Progress | For time being we hardcoded system mac ID of POS machine
10 | Show customer details in Payment screen | Soma | Not yet Started
11 | Hide UserId column in the Users screen | Soma | Not yet Started | There is no login for standard users.
12 | New feature to adjust the payments between customers | Soma | Not yet Started
13 | Encrypt few column in the Invoice table in the database | Soma | Not yet Started
Improvements :
S.No | Task Description | Responsible | Status | Remarks
1 | We can integrate Exception handling to see the list of application issues. | Soma | Not yet started | Datewise log file will be created
2 | UI improvement need to taken care | Soma | Not yet started | Due to hardcoding few controls height and widths, UI is not properly rendered in different screen sizes
Action Items :
S.No | Task Description | Responsible | Status | Remarks
1 | Analyze source code | Soma | In-Progress
2 | Setup local database | Soma | Completed
3 | Setup local environment | Soma | Completed | Development environment
4 | Create testing environment to test by the end-user(Suresh Shenoy) | Nichi | Not yet Started | Max 10 members can login into VM

## Issue List
S.No | Issue Description
1 | In PayForm next to Scan ID field "Search" button is missing
2 | In UpdateInventoryForm.cs file capturing image source code is commented in "pictureButton_Click" method
3 | In AdhocItemForm.cs file commented source code from line 128~208
4 | In CreditCardCashForm.cs file commented source code from Line no 68~86
5 | In InventoryFormcs file commented source code few lines
6 | In PayForm.cs file commented source code few lines
7 | In Invoice table for few records Company Name is null, due to this print form is not showing header value

## Release History
#No | Date | Details | Status | Deployed | Tested | Responsible | Remarks
1 | 2021-04-02 | 1. Added POS machine mac ID (0060EF1C0266) 2. After entering Inventory Id and then press enter, data should be loaded from database. | Released | yes | yes | Dinesh/Suresh | Unable to run the application due to db connection issues
2 | 2021-04-05 | 1. Database connection issue resolved | Released | yes | yes | Dinesh/Suresh | Application is running successfully in POS system